## Project Schedule
Task | Start Date | End Date | Duration (Days) | Owner | Status
Project Kickoff | 01-Aug-2026 | 02-Aug-2026 | 2 | Project Manager | Completed
Requirements Gathering | 03-Aug-2026 | 10-Aug-2026 | 8 | Business Analyst | Completed
Design Phase | 11-Aug-2026 | 20-Aug-2026 | 10 | UI/UX Team | Completed
Development | 21-Aug-2026 | 25-Sep-2026 | 36 | Development Team | In Progress
Testing | 26-Sep-2026 | 10-Oct-2026 | 15 | QA Team | Pending
Deployment | 12-Oct-2026 | 15-Oct-2026 | 4 | DevOps | Pending