## Change Request Log
CR ID | Request Date | Requested By | Change Description | Business Impact | Approval Status | Implementation Status
CR001 | 05-Aug-2026 | Client | Add wishlist feature | Medium | Approved | Completed
CR002 | 07-Aug-2026 | Project Manager | Revise reporting dashboard | High | Pending | Not Started
CR003 | 10-Aug-2026 | Business Analyst | Update user registration flow | Medium | Approved | In Progress
CR004 | 12-Aug-2026 | Sponsor | Enhance payment security | High | Approved | Planned